## 📅 Master Roadmap
VitalHealth – Digital Twin ¦ 6-Month Development Roadmap
[6 empty] | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026
SI.no | Category | Feature / Task | Reason | Priority | Effort (days) | Jun | Jul | Aug | Sep | Oct | Nov | Status
PHASE 1: Stability & Core Polish
1 | BioGears Engine | Fix silent crash & pathing bugs | Prevents application from crashing unexpectedly during simulation |  | 10
2 | BioGears Engine | Chunked time-advancement (no hangs) | Ensures the UI remains responsive during long simulation calculations |  | 8
3 | BioGears Engine | XML schema validation pipeline | Validates engine configurations before runtime to prevent bad states |  | 6
4 | BioGears Engine | Concurrency guard (no overlapping jobs) | Avoids engine race conditions when multiple actions are triggered |  | 5
5 | BioGears Engine | State backup & rollback on failure | Ensures user simulation progress is not lost if a crash occurs |  | 5
6 | Mobile App | Bold AI response rendering | Improves readability of AI-generated insights for users |  | 2
7 | Mobile App | Background job persistence on restart | Keeps simulation tasks running even if the user closes the app |  | 4
PHASE 2: Wearable & Data Integration
8 | Wearables | Apple Health / Google Fit full sync | Automatically populates the twin with steps, heart rate, and sleep |  | 14
9 | Wearables | Garmin & Fitbit API integration | Expands compatibility for users with dedicated fitness trackers |  | 10
10 | Wearables | Continuous glucose monitor (CGM) feed | Automates blood glucose tracking for accurate metabolic simulation |  | 8
11 | Wearables | Wearable → BioGears real-time input | Uses live patient data to continuously recalibrate the twin's state |  | 12
12 | Clinical Data | HL7 FHIR record import | Pulls in verified clinical history from the user's healthcare provider |  | 10
13 | Clinical Data | PDF lab report OCR + parsing | Allows manual import of blood work and lab results from photos |  | 8
14 | Mobile App | Offline mode with local SQLite cache | Ensures app remains functional in areas with poor internet connection |  | 7
PHASE 3: Simulation Accuracy
15 | BioGears Engine | Multi-substance concurrent dosing support | Allows realistic scenarios where a patient takes multiple medications |  | 10
16 | BioGears Engine | Full substance registry (50+ drugs) | Expands the medical accuracy and utility of the digital twin |  | 8
17 | BioGears Engine | Pharmacokinetic unit validation | Ensures drug absorption and clearance match real-world medical data |  | 6
18 | BioGears Engine | Real-time vitals streaming (SSE) | Provides instant, continuous physiological feedback to the user |  | 7
19 | BioGears Engine | Blood glucose & insulin model | Crucial for diabetic users to predict sugar levels based on diet |  | 10
20 | AI / Analytics | Physiology anomaly detection (ML) | Identifies abnormal health patterns before they become critical |  | 12
PHASE 4: AI & Personalisation
21 | AI / Analytics | Personalised risk score engine | Gives the user a simple, holistic metric of their overall health |  | 14
22 | AI / Analytics | Symptom → differential diagnosis RAG | Provides context-aware possible conditions when a user feels unwell |  | 12
23 | AI / Analytics | Medication interaction checker | Warns users of dangerous side effects when mixing prescriptions |  | 10
24 | AI / Analytics | Predictive health trend forecasting | Shows the user where their health is heading in the next 3-6 months |  | 14
25 | Mobile App | AI-generated weekly health report PDF | Summarizes weekly progress and simulation insights into a shareable format |  | 8
26 | Mobile App | Smart notification triggers (anomaly alert) | Actively alerts the user when their digital twin enters a dangerous state |  | 6
27 | Mobile App | Multilingual support (5 languages) | Broadens user base to non-English speaking demographics |  | 10
PHASE 5: Family & Social Features & Research
28 | Family Health | Family dashboard (shared vitals view) | Allows monitoring the health of aging parents or dependents |  | 10
29 | Family Health | Guardian alerts for elderly/child members | Notifies a family member instantly if a loved one's vitals drop |  | 8
30 | Family Health | Role-based access control (RBAC) | Ensures privacy by controlling what data family or doctors can see |  | 7
31 | Family Health | Shared medication schedule | Helps caretakers ensure dependents are taking their medication on time |  | 6
32 | Clinical | Telemedicine / doctor share report flow | Easily sends the digital twin's data directly to a physician |  | 10
33 | Clinical | Emergency SOS with location + vitals | Saves lives by dispatching paramedics with the user's live health data |  | 8
34 | Security | End-to-end encryption (HIPAA prep) | Critical requirement for safely storing and transmitting medical data |  | 12
35 | Research | Draft & submit academic paper | Publish digital twin architecture and clinical accuracy results in a peer-reviewed journal |  | 15
PHASE 6: Scale, Launch & Monetisation
36 | Infrastructure | Kubernetes auto-scaling for BioGears | Handles high user load by spinning up simulation servers dynamically |  | 14
37 | Infrastructure | CI/CD pipeline (GitHub Actions + EAS) | Automates testing and deployment to speed up development cycles |  | 8
38 | Infrastructure | HIPAA compliance audit & penetration test | Legally required to store patient data and operate in the healthcare space |  | 14
39 | Infrastructure | Production monitoring (Grafana/Sentry) | Allows the engineering team to detect and fix bugs in real-time |  | 8
40 | Monetisation | Freemium tier + subscription paywall | Generates recurring revenue to sustain server and development costs |  | 10
41 | Monetisation | B2B clinic / hospital dashboard | Expands revenue by selling the platform to healthcare providers |  | 14
42 | Launch | App Store & Play Store submission | Makes the product officially available to the public for download |  | 5
43 | Launch | Beta user onboarding & feedback loop | Gathers critical user insights before the massive public launch |  | 7

## 🗓 Sprint Plan
VitalHealth – 2-Week Sprint Breakdown (Phase 1 & 2 detailed)
Sprint | Dates | Focus | Key Deliverables | Owner | Effort | Done?
S-01 | May 11–24 | Engine Stability | Fix pathing bugs, silent crash detection, XML validation, concurrency guard | Backend | 18 days | 🔄
S-02 | May 25–Jun 7 | Mobile Hardening | Background job persistence, push notification on job complete, BioGears streaming | Full-Stack | 16 days | 📋
S-03 | Jun 8–21 | Wearables I | Apple Health sync, Google Fit sync, Garmin API, wearable → BioGears input | Mobile | 20 days | 📋
S-04 | Jun 22–Jul 5 | Clinical Data | HL7 FHIR import, PDF OCR lab reports, offline SQLite cache | Full-Stack | 16 days | 📋
S-05 | Jul 6–19 | Substance & PK | 50+ drug registry, multi-substance dosing, PK unit validation, glucose model | Backend | 20 days | 📋
S-06 | Jul 20–Aug 2 | Real-Time Vitals | SSE vitals stream, SSE mobile client, anomaly ML model v1 | Full-Stack | 18 days | 📋
S-07 | Aug 3–16 | AI Engine | Personalised risk score, symptom RAG diagnosis, medication interaction checker | AI/ML | 22 days | 📋
S-08 | Aug 17–30 | Predictive Health | Trend forecasting model, weekly PDF report gen, smart anomaly alerts | AI/ML | 20 days | 📋
S-09 | Sep 1–14 | Family Features | Family dashboard, guardian alerts, RBAC, shared medication schedule | Full-Stack | 18 days | 📋
S-10 | Sep 15–28 | Compliance, SOS & Research | SOS with vitals, E2E encryption, telemedicine share flow, draft academic paper | Security/Research | 20 days | 📋
S-11 | Oct 1–14 | Scale & Infra | Kubernetes autoscaling, CI/CD pipeline, Grafana monitoring, Sentry | DevOps | 18 days | 📋
S-12 | Oct 15–31 | Launch & Monetise | Subscription paywall, App Store submission, B2B dashboard, beta feedback loop | All | 22 days | 📋

## ⚡ Priority Matrix
Feature Priority Matrix – Impact vs Effort
Feature | Category | Impact (1-10) | Effort (1-10) | Priority Score | Quadrant
Fix BioGears silent crash & pathing | Engine | 10 | 3 | 17 | 🚀 Quick Win
Real-time vitals streaming (SSE) | Engine | 9 | 5 | 13 | 🚀 Quick Win
Wearable → BioGears live input | Wearables | 10 | 7 | 13 | 💎 Strategic
Personalised risk score engine | AI/ML | 10 | 8 | 12 | 💎 Strategic
Symptom RAG differential diagnosis | AI/ML | 9 | 7 | 11 | 💎 Strategic
HL7 FHIR clinical record import | Clinical | 8 | 6 | 10 | 💎 Strategic
Apple Health / Google Fit sync | Wearables | 9 | 5 | 13 | 🚀 Quick Win
Blood glucose & insulin model | Engine | 8 | 7 | 9 | 💎 Strategic
Medication interaction checker | AI/ML | 9 | 6 | 12 | 💎 Strategic
Emergency SOS with vitals | Clinical | 10 | 4 | 16 | 🚀 Quick Win
HIPAA E2E encryption | Security | 10 | 8 | 12 | 💎 Strategic
Family guardian alerts | Family | 8 | 5 | 11 | 🚀 Quick Win
Weekly health report PDF | AI/ML | 7 | 4 | 10 | 🚀 Quick Win
Subscription paywall | Monetisation | 9 | 5 | 13 | 🚀 Quick Win
B2B clinic dashboard | Monetisation | 8 | 8 | 8 | 🎯 Long-term
Multilingual support | UX | 6 | 6 | 6 | 🎯 Long-term
Kubernetes autoscaling | Infra | 8 | 7 | 9 | 💎 Strategic
CI/CD pipeline | Infra | 7 | 4 | 10 | 🚀 Quick Win
PDF OCR lab report parsing | Clinical | 7 | 5 | 9 | 🚀 Quick Win
Offline SQLite cache | Mobile | 7 | 5 | 9 | 🚀 Quick Win
Draft & submit academic paper | Research | 10 | 8 | 12 | 💎 Strategic

## 📊 KPI Targets
VitalHealth – KPI & Success Metrics by Month
KPI / Metric | Baseline | May | Jun | Jul | Aug | Sep | Oct (Target)
BioGears Sim Success Rate (%) | ~55% | 85% | 92% | 95% | 97% | 98% | 99%
Avg Sim Completion Time (min) | 8–12 min | 6 min | 4 min | 3 min | 2 min | 2 min | <2 min
App Crash Rate (%) | ~5% | 3% | 2% | 1.5% | 1% | 0.5% | <0.5%
Wearable Data Sources Supported | 1 | 1 | 1 | 4 | 6 | 8 | 10+
Substances Supported in Engine | ~20 | 20 | 50 | 60 | 70 | 70 | 80+
AI Diagnosis Accuracy (RAG %) | N/A | N/A | N/A | N/A | 75% | 82% | 88%
Active Beta Users | 0 | 10 | 50 | 150 | 400 | 800 | 2,000
Family Members Per Account (avg) | 1 | 1 | 1.2 | 1.5 | 2 | 2.5 | 3+
Push Notification Open Rate (%) | N/A | 30% | 35% | 38% | 40% | 42% | 45%
Monthly Active Users (MAU) | 0 | 20 | 80 | 200 | 500 | 1,200 | 3,000
App Store Rating | N/A | N/A | N/A | N/A | N/A | N/A | 4.6+
Revenue (MRR $) | $0 | $0 | $0 | $0 | $500 | $2,000 | $8,000